## Sheet1
PRC Monument Ridge Comments
2025-12-18
SWMP Section | Issue Requiring Resolution | Response | Source
Section 1. Site and Project Description | Discrepancy in the anticipated area of disturbance. The SWMP states 34 Acres, but associated ESQCP forms list 50 acres and 59.5 acres. | I updated the site description to reflect 59.5 total acres and 50 acres of disturbance to ensure consistency with the ESQCP form. | SWMP Redlines
Section 6 & 12.1.9 (Soils/Groundwater) | Shallow groundwater is present in pond locations. Reviewers require the SWMP to reflect a specific mitigation strategy rather than just noting the permit requirement. | RAY - STILL NEEDS TO BE ADDRESSED (which grounwater mitagation method was used) | SWMP Redlines
Section 7. Non-Stormwater Discharge | The internal cross-reference to the "Final Drainage Report" page number is outdated. | I updated the reference page number to 7 | SWMP Redlines
Section 5 (Construction Phasing). | Revised Project Schedule: | I shifted the construction start date to February 1, 2026, and updated the timelines for all four construction stages accordingly.
Section 5 (Construction Phasing) | TSB Phasing | I integrated the use of Temporary Sediment Basins (TSBs) to be operational prior to major overlot grading.
Section 12.1.1 (CMs for Disturbed Soil/Sediment) | TSB Technical Sizing | I provided a technical sizing table and operational requirements for TSBs (1, 2, and 3) based on upstream drainage area and required hole diameters.
Section 15.3 (CM Maintenance Procedures) | TSB Maintenance | I added a new maintenance section for TSBs requiring weekly inspections and sediment removal once it reaches 50% of the basin's design capacity.