## Sheet1
PRC Review Comments | Date
EPC Stormwater Review Comments | 2025-06-24
Monument Ridge East Filing 1 (SF2514)
Comment | Page (Original) | Response | Page (Updated)
Item 1. Add Qualified Stormwater Manager and Contractor Information to cover/title sheet. If unknown, add a placeholder to be updated prior to the pre-construction meeting: QUALIFIED STORMWATER MANAGER Name: Company: Address: CONTRACTOR Name: Company: Address: | 1 | The Qualified Stormwater Manager (Kelsey Crowder, Elkhorn Enviro) and Contractor (NB Trenchless) information has been added to the cover/title sheet. | 1
Note: While EPC currently does not have criteria specifying what information must be included on the self-inspection reports, the inspection report template you have provided does not meet CDPS COR400000 requirements. Refer to COR400000 Part I.D.5.c for State requirements. No change required to meet EPC requirements. | 4 | The inspection report was changed to the template provided with COR4000000 | 37
SWMP Checklist Item B. Add "CDPS General Permit COR4000000 Certification and Copy of General Permit" to list of Appendices and create a placeholder in the Appendices | 4 | "CDPS General Permit COR4000000 Certification and Copy of General Permit" has been added to the list of Appendices. | 4
SWMP Checklist Item C. Add "Erosion and Stormwater Quality Control Permit (ESQCP) Stormwater Permit Form" to list of Appendices and create a placeholder in the Appendices | 4 | "Erosion and Stormwater Quality Control Permit (ESQCP) Stormwater Permit Form" has been added to the list of Appendices. | 4
SWMP Checklist Item D. Add "Other CDPHE Permit Certifications" to list of Appendices and create a placeholder in the Appendices. Per drainage report, a groundwater dewatering permit is needed. | 4 | "Other CDPHE Permit Certifications" has been added to the list of Appendices. The SWMP now clarifies that if shallow groundwater is encountered, proper permits will be obtained for any groundwater discharge prior to construction. | 4, 9, 11, 23
SWMP Checklist Item 6. State the total acreage of the site and the acreage anticipated to be disturbed by clearing, excavation, grading, and any other construction activities. | 5 | The total project area (approximately 65 acres) and anticipated disturbed area (34 acres) have been stated in the "Site and Project Description" section. | 5
SWMP Checklist Item 8. Verify the current percent cover from native vegetation on the site. 21% is inconsistent with EPC's review of site via satellite imagery. | 5 | The estimated vegetation cover has been updated to roughly 39 percent of the site, determined using aerial imagery from Google Earth dated May 2025. | 5
SWMP Checklist Item 20. Update language to reflect current CDPHE Final Stabilization requirements for areas using vegetative cover: In areas where final stabilization will be achieved using vegetative cover, vegetative must be evenly distributed perennial vegetation and coverage will be, at a minimum, equal to 70% of what would have been provided by native vegetation in a local, undisturbed area or adequate reference site. | 6 | The language for final stabilization has been updated to reflect CDPHE requirements, stating that evenly distributed perennial vegetation coverage must be at least 70% of what would have been provided by native vegetation in a local, undisturbed area or adequate reference site. | 6, 26
SWMP Checklist Item 5. Identify the specific CMs (per the submitted GEC Plan) associated with each construction activity so it's clear when each CM will be installed. See Table CP-1 in MHFD detail (SM-1 for guidance. | 6 | The document now explicitly lists specific CMs associated with each construction phase (Pre-Disturbance Stage, Overlot Grading, Infrastructure and Building Construction, Final Stabilization). | 6-10
Include the anticipated starting and completion dates for each major construction activity, including the anticipated date in which final stabilization will be achieved lately after grading or earth disturbance has occurred. All temporary soll erosion Control Measures and Control Measures shall be maintained until site reaches final stabilization and permanent soil erosion Control Measures are implemented. | 6 | Anticipated start and completion dates for the overall project and for each construction phase have been included. The document also reiterates that temporary soil erosion control measures will be maintained until final stabilization is achieved. | 6, 7, 8, 9, 10
SWMP Checklist Item 7. Describe the erodibility of the identified soils. | 7 | The erodibility of the identified soils (Alamosa loam and Peyton-Pring complex) is now described. | 10-11
SWMP Checklist Item 8. This statement is inconsistent with EPC's review of site via satellite imagery. Verify the current percent cover from native vegetation on the site. | 7 | The estimated vegetation cover has been updated to roughly 39 percent of the site, determined using aerial imagery from Google Earth dated May 2025. The description of the ground cover based on this imagry has also been revised. | 5,11
No soil borings or groundwater tests have been done for this site. This is inconsistent with info provide in drainage report. (This is inconsistent with info provide in drainage report). | 7 | The document now states that a groundwater determination has been made, indicating shallow groundwater in pond areas, and that proper permits will be obtained for groundwater discharge prior to construction. | 11-12
Incorrect county. | 7 | The county in Table 1 has been corrected to "El Paso County Area, Colorado". | 11
SWMP Checklist Item 9. Discharge of concrete wash water to ground (e.g. a concrete washout area) is an allowable non-stormwater discharge per the COR400000 Permit if properly identified in the SWMP and if the appropriate control measures are implemented. Revise discussion. Reference COR400000 Part I.A.1.b.ii for more information if needed. | 7 | The discussion on non-stormwater discharge now explicitly references CDPS General Permit COR400000 Part I.A.1.b.ii regarding the discharge of concrete washout water to the ground and states that concrete washout locations must not be situated where shallow groundwater may be present. | 11-12
SWMP Checklist Item 9. Drainage report pg. 7 states that groundwater is anticipated and a permit will be required. | 7 | The SWMP now explicitly states that groundwater is anticipated, particularly in areas designated for pond construction, and that proper permits will be obtained for any groundwater discharge prior to construction. | 11-12
SWMP Checklist Item 10. This area is located within the project area. Describe how stormwater leaves the site. Reference Checklist for full description requirements. | 7 | The "Receiving waters" section has been expanded to describe how stormwater is managed and conveyed off-site through a comprehensive system of engineered control measures, including collection systems, Extended Detention Basins (EDBs), and flow routing/outfalls. | 12-13
SWMP Checklist Item 10. Verify state water receiving stormwater discharges from the site. Site flows north but Monument Creek is SW of site? | 7 | The SWMP clarifies that while the site generally flows north, Monument Creek serves as the ultimate receiving water for the Bald Mountain major drainage basin, which encompasses the project area. | 12
Change "GEC Administrator" to "Qualified Stormwater Manager" for consistency with El Paso County ECM. | 8 | All instances of "GEC Administrator" have been changed to "Qualified Stormwater Manager". | 9, 13, 14, 22, 25, 27, 28, 29, 30, 33, 34
SWMP Checklist Item 12. Update information to be relevant to this project. | 9 | The "Identification of Potential Pollution Sources" section has been updated to be more relevant to the project, with expanded descriptions for disturbed/stored soils, vehicle tracking, and waste management practices, clarifying their applicability to this project. | 14-15
SWMP Checklist Item 12. Exposed/disturbed soil is a potential source of pollution for this project. | 9 | This statement has been explicitly added under "All disturbed and stored soils" in the "Identification of Potential Pollution Sources" section. | 14
SWMP Checklist Item 12. Per the COR400000 Permit, the following 7. Significant dust or pollution sources must be identified in the SWMP as they apply to all is to be expected duri construction sites: disturbed and stored soils, vehicle tracking of sediments, and on-site waste management practices. | 9 | The SWMP now identifies "Significant dust or particulate generating processes" (dust from exposed soils) and "On-site waste management practices" as potential pollution sources applicable to this project, along with disturbed and stored soils and vehicle tracking. | 14-15
SWMP Checklist Item 12. Is this applicable to this project? | 9 | The SWMP now states that "Other areas or procedures where potential, spills can occur" are "None other are known at this time." | 15
SWMP Checklist Item 15/16. Update info to be relevant to this project. Should have narrative description of all structural/non-structural CMs as shown on submitted PRC Engineering GEC Plan. Additionally, a TSB will be required but is not shown on submitted GEC. | 12 | The "Control Measures Overview" section has been significantly expanded to provide narrative descriptions of all structural and non-structural CMs, including Temporary Sediment Basins (TSBs) / Permanent Extended Detention Basins (EDBs), perimeter silt fences, inlet protection, erosion control blanketing, stabilized construction site entrances, and more. | 18-20
SWMP Checklist Item 15/16 Update info to be relevant to this project. | 13 | The "CMs for Stored Materials" and "CMs for Vehicle Tracking and Loading/Unloading" sections have been updated to be more relevant to this project, with specific details on stockpile management, erosion control, stabilization, and daily maintenance practices for vehicle tracking. | 20-21
SWMP Checklist Item 16. Add text stating that water used for dust suppression may not be allowed to discharge off-site. | 13 | Text has been added to the "CMs for Dust" section stating that "Water used for dust suppression may not be allowed to discharge off-site." | 21
SWMP Checklist Item 15/16 Update info to be relevant to this project. | 14 | CMs for Vehicle Tracking and Loading/Unloading have been updated. | 21-22
SWMP Checklist Item 16. Add text stating: dustrial Waste Portable toilets will be located a minimum SWMP Checklist Item 15/16. Update info to be relevant to this project. of 10ft from stormwater inlets and 50ft practices will be implemented to maintain a project site free from state waters. They will be secured at sh receptacles will be inspected regularly to ensure they all four corners to prevent overturning and y when full and that debris stays contained within the cleaned on a weekly basis. They will be | 14 | The "CMs for Non-Industrial Waste" section has been updated to include specific details for portable toilets, such as their minimum distance from stormwater inlets (10ft) and state waters (50ft), securing them against overturning, weekly cleaning, and daily spill inspections. | 22
SWMP Checklist Item 15/16. Update info to be relevant to this project. | 14 | Removed "Portable toilets located within Colorado Springs ROW will be anchored on a trailer: as required." | 23
SWMP Checklist Item 15/16. All CMs shown on submitted GEC are not discussed here. | 15 | The "Phasing of Control Measures" section now provides a more comprehensive discussion of CMs for each phase, including Stabilized Staging Areas, Stabilized Construction Site Entrance, Vehicle Tracking Controls, Silt Fences, Inlet Protection, Concrete Washout Areas, Stockpile Protection, Erosion Control Blanketing, Straw Wattles/Rock Socks, and others. | 24-26
Clarify that they can be removed once Final Stabilization is achieved. | 16 | The document now explicitly states that Temporary Control Measures will be removed once Final Stabilization is achieved. | 26
SWMP Checklist Item 19. Landscape plan indicates hardscaping in several areas, need to list all final stabilization measures in SWMP. | 16 | The "Control Measures for Final Stabilization" section has been updated to list permanent surfaces (concrete, asphalt, seed/mulch) and landscaping as final stabilization measures. | 9-10
SWMP Checklist Item 21. Update info to be relevant to this project. | 16 | Changed to reflect the long-term control measures (EDB's). | 10, 26-27
SWMP Checklist Item 19. Is this applicable to this project? | 16 | Removed rip-rap bank stabilization. | 32
SWMP Checklist Item 20. Not just noxious weeds, but all weeds. | 16 | The language has been updated to specify that "weeds do not count towards the 70% revegetation" for final stabilization. | 26, 32
Update to "Qualified Stormwater Manager" for consistency with El Paso County ECM. | 16 | All instances of "GEC Manager" have been changed to "Qualified Stormwater Manager". | 22, 25, 28, 29, 30, 33, 34
SWMP Checklist Item 20. Include a statement that in areas where final stabilization will be achieved using vegetative cover, vegetative must be evenly distributed perennial vegetation and coverage will be, at a minimum, equal to 70% of what would have been provided by native vegetation in a local, undisturbed area or adequate reference site. | 16 | This exact statement has been included in the "Control Measures for Final Stabilization" section. | 26
SEMSWA is not applicable to this project. Change to El Paso County | 17 | All instances of "SEMSWA" have been changed to "El Paso County" for consistency. | 28, 29, 30
Change all instances of "GESC Manager" to "Qualified Stormwater Manager" for consistency with El Paso County ECM. | 17 | All instances of "GESC Manager" have been changed to "Qualified Stormwater Manager". | 22, 25, 28, 29, 30, 33, 34
Change all instances of "GESC Plan" to "GEC Plan" for consistency with El Paso County ECM. | 17 | All instances of "GESC Plan" have been changed to "GEC Plan". | 21, 28, 29, 30, 33, 34
SWMP Checklist Item 20. Update to: vegetative cover must be evenly distributed perennial vegetation and coverage will be, at a minimum, equal to 70% of what would have been provided by native vegetation in a local, undisturbed area or adequate reference site. | 18 | This exact statement has been included in the "Control Measures for Final Stabilization" section. | 26
SEMSWA is not applicable to this project. Change all instances to El Paso County | 19 | All instances of "SEMSWA" have been changed to "El Paso County" for consistency. | 28, 29, 30
SEMSWA is not applicable to this project. Change all instances to El Paso County | 19 | All instances of "SEMSWA" have been changed to "El Paso County" for consistency. | 28, 29, 30
SWMP Checklist Item 23. Clarify that inactive site inspections must be performed at least once every 30-days | 21 | Inspect seeded and mulched areas, as well as stormwater management system, at least once every 30-days. | 32
Change all instances of "GEC Inspector" to "County Stormwater Inspector" | 21 | All instances of "GEC Inspector" have been changed to "County Stormwater Inspector". | 32
SWMP Checklist Item 20. Not just noxious weeds, but all weeds. | 21 | Changed to just "weeds". | 32
Change to El Paso County | 21 | Changed to El Paso County | 32
SWMP Checklist Item 24. Add text stating that self-inspection reports must include the Qualified Stormwater Manager's signature. | 22 | The section title "15.2 Self-Inspections" has been updated to explicitly state "(must include the Qualified Stormwater Manager's signature)". The inspection report template also includes a signature line for the Qualified Stormwater Manager. | 33, 44
SWMP Checklist Item 23. This is inconsistent with the inspection frequency you've identified on pdf pg. 16 and 21. Please clarify the intended self-inspection frequency. | 22 | The self-inspection frequency has been clarified. It states that the Qualified Stormwater Manager shall make a thorough inspection at least once every 7 calendar days, with post-storm event inspections within 24 hours, or alternatively, self-inspections every 7 calendar days foregoing post-storm events. For completed areas awaiting final stabilization, inspections are required at least once every 30 days. | 33-34
Change all instances of "GEC Administrator" to "Qualified Stormwater Manager" for consistency with El Paso County ECM. | 22 | All instances of "GEC Administrator" have been changed to "Qualified Stormwater Manager". | 9, 13, 14, 22, 25, 27, 28, 29, 30, 33, 34
Remove. This is not applicable to erate as needed to comply with the GEC Plan. El Paso County Projects.as steep grades and close proximity to a state water are reasons for increasing the frequency of self- inspections. | 22 | The section of text has been removed. | 33
Change to County Stormwater Inspector | 22 | The phrase has been updated to "County Stormwater Inspectors will review self-inspections during County compliance inspections." | 33
SWMP Checklist Item. Change to "at least once every 30-days" | 22 | The self-inspection frequency for sites or portions of sites where construction activities are completed but final stabilization has not yet been achieved is now stated as "at least once every 30-days". | 34
SWMP Checklist Item. Change to "at least once every 30-days" | 23 | The self-inspection frequency for sites or portions of sites where construction activities are completed but final stabilization has not yet been achieved is now stated as "at least once every 30-days". | 34
Remove. Not applicable to County criteria. | 23 | The section of text has been removed. | 34
SWMP Checklist Item 22. Add text stating that The QSM shall amend the SWMP when there is a change in design, construction, change in sources of pollutants, O&M of the site which would require the implementation of new or revised CMs or if the SWMP proves to be ineffective in achieving the general objectives of controlling pollutants in SW discharges associated with construction activity or when CMs are no longer necessary and are removed. SWMP amendments or updates must include a notation in the SWMP identifying the date and description of the change. Methods for notation may include notations on the site map (i.e. GEC Plan), a log of changes, redline changes in the SWMP, or other measures. | 23 | This exact text has been added to the "Record Keeping Procedures" section. | 34
SWMP Checklist Item 24. Add text to clarify that the SWMP (to include the self-inspection reports and GEC Plan) are to be available to the County Stormwater Inspector on-site or electronically throughout the duration of the project. The documents may be kept electronically if the SWMP is immediately accessible to the inspector during an inspection to the same extent as a paper copy stored at the site would be. | 23 | This exact text has been added to the "Record Keeping Procedures" section. | 34