## FAE
2021 Financial Assurance Estimate Form
(with pre-plat construction) | [7 empty] | Updated: 12/22/2020
PROJECT INFORMATION
Latigo Trails Fil 9 |  |  |  | 4444800% |  |  | SF-XX-XXX
Project Name |  |  |  | Date |  |  | PCD File No.
|  |  |  | Unit |  |  | (with Pre-Plat Construction)
Description |  | Quantity | Units | Cost |  | Total | % Complete | Remaining
SECTION 1 - GRADING AND EROSION CONTROL (Construction and Permanent BMPs) | [9 empty] | Note
* Earthwork | [8 empty] | *
*
less than 1,000; $5,300 min |  |  | CY | 8 | = | 0 |  | 0 | *
1,000-5,000; $8,000 min |  |  | CY | 6 | = | 0 |  | 0 | *
5,001-20,000; $30,000 min |  |  | CY | 5 | = | 0 |  | 0 | *
20,001-50,000; $100,000 min |  | 49065 | CY | 3.5 | = | 171727.5 |  | 171727.5 | *
50,001-200,000; $175,000 min |  |  | CY | 2.5 | = | 0 |  | 0 | * | Net (cut=49065, fill=20768)
greater than 200,000; $500,000 min |  |  | CY | 2 | = | 0 |  | 0 | *
* Permanent Seeding (inc. noxious weed mgmnt.) |  | 24.4 | AC | 828 | = | 20203.2 |  | 20203.2 | * | 24.375
* Mulching |  |  | AC | 777 | = | 0 |  | 0 | *
* Permanent Erosion Control Blanket |  | 3053 | SY | 6 | = | 18318 |  | 18318 | *
* Permanent Pond/BMP Construction |  | See Below | CY | 0 | = |  |  | 0 | *
* Permanent Pond/BMP (provide engineer's estimate) |  |  | EA |  | = | 0 |  | 0 | *
Safety Fence |  |  | LF | 3 | = | 0 |  | 0 | *
Temporary Erosion Control Blanket |  |  | SY | 3 | = | 0 |  | 0
Vehicle Tracking Control |  | 2 | EA | 2453 | = | 4906 |  | 4906
Silt Fence |  | 2500 | LF | 2.6 | = | 6500 |  | 6500
Temporary Seeding |  |  | AC | 650 | = | 0 |  | 0
Temporary Mulch |  |  | AC | 777 | = | 0 |  | 0
Erosion Bales |  |  | EA | 26 | = | 0 |  | 0
Erosion Logs/Straw Waddle |  |  | LF | 5 | = | 0 |  | 0
Rock Check Dams |  | 183 | EA | 518 | = | 94794 |  | 94794 |  | located every 100' for now
Inlet Protection |  | 4 | EA | 173 | = | 692 |  | 692
Outet Protection |  | 5 | EA | 173 |  | 865 |  | 865
Sediment Basin |  |  | EA | 1824 | = | 0 |  | 0
Concrete Washout Basin |  | 1 | EA | 932 | = | 932 |  | 932
[5 empty] | = | 0 |  | 0
[insert items not listed but part of construction plans] | [5 empty] | 0 |  | 0
G-18 Pond - Permanent | [5 empty] | 0 |  | 0
Detention Outlet Structure |  | 1 | EA | 5000 | = | 5000 |  | 5000
Concrete/Riprap Forebay |  |  | EA | 3000 | = | 0 |  | 0
Concrete Trickle Channel |  |  | CY | 95 | = | 0 |  | 0
Detention Emergency Spillway |  | 1 | EA | 5000 |  | 5000 |  | 5000
Permanent WQ Feature (EDB) |  |  | EA | 5000 |  | 0 |  | 0
Gravel Maintenance Access Road |  | 400 | SY | 45 |  | 18000 |  | 18000
Black Squirrel Pond - Interim | [5 empty] | 0 |  | 0
Detention Outlet Structure |  | 1 | EA | 10000 | = | 10000 |  | 10000
Concrete/Riprap Forebay |  |  | EA | 3000 | = | 0 |  | 0
Concrete Trickle Channel |  |  | CY | 95 | = | 0 |  | 0
Detention Emergency Spillway |  | 1 | EA | 10000 |  | 10000 |  | 10000
Permanent WQ Feature (EDB) |  |  | EA | 5000 |  | 0 |  | 0
Gravel Maintenance Access Road |  | 800 | SY | 45 |  | 36000 |  | 36000
|  |  |  | MAINTENANCE (35% of Construction BMPs) | = | 67441.15 |  | 67441.15
* - Subject to defect warranty financial assurance. A minimum of 20% shall be retained until final acceptance (MAXIMUM OF 80% COMPLETE ALLOWED) |  | Section 1 Subtotal |  |  | = | 470378.85 |  | 470378.85
SECTION 2 - PUBLIC IMPROVEMENTS *
ROADWAY IMPROVEMENTS
*
Mobilization/Construction Traffic Control |  | 1 | LS | 50000 | = | 50000 |  | 50000 | *
Removal of Asphalt (Full Depth) |  |  | SY | 10 |  | 0 |  | 0 | *
Removal of Asphalt (Planing-4") |  |  | SY | 5 |  | 0 |  | 0 | *
Removal of Striping |  |  | LF | 1 |  | 0 |  | 0 | *
Removal of Fencing |  |  | LF | 5 |  | 0 |  | 0 | *
Aggregate Base Course (135 lbs/cf) |  |  | Tons | 29 | = | 0 |  | 0 | *
Aggregate Base Course (135 lbs/cf) |  | 3071.1852 | CY | 52 |  | 159701.6296 |  | 159701.6296 | *
Asphalt Pavement (3" thick) |  |  | SY | 14.5 |  | 0 |  | 0 | *
Asphalt Pavement (4" thick) |  | 18427.85 | SY | 20 |  | 368557 |  | 368557 | *
Asphalt Pavement (6" thick) |  |  | SY | 30 |  | 0 |  | 0 | *
Asphalt Pavement (147 lbs/cf) | " thick |  | Tons | 91 | = | 0 |  | 0 | *
Raised Median, Paved |  |  | SF | 8.3 | = | 0 |  | 0 | *
Regulatory Sign/Advisory Sign |  | 6 | EA | 311 | = | 1866 |  | 1866 | *
Guide/Street Name Sign |  | 6 | EA | 250 | = | 1500 |  | 1500 | *
Epoxy Pavement Marking |  |  | SF | 14 | = | 0 |  | 0 | *
Thermoplastic Pavement Marking |  |  | SF | 24 | = | 0 |  | 0 | *
Barricade - Type 3 |  | 2 | EA | 207 | = | 414 |  | 414 | *
Delineator - Type I |  |  | EA | 25 | = | 0 |  | 0 | *
Curb and Gutter, Type A (6" Vertical) |  |  | LF | 31 | = | 0 |  | 0 | *
Curb and Gutter, Type B (Median) |  |  | LF | 31 | = | 0 |  | 0 | *
Curb and Gutter, Type C (Ramp) |  |  | LF | 31 | = | 0 |  | 0 | *
4" Sidewalk (common areas only) |  |  | SY | 50 | = | 0 |  | 0 | *
5" Sidewalk |  |  | SY | 62 | = | 0 |  | 0 | *
6" Sidewalk |  |  | SY | 75 | = | 0 |  | 0 | *
8" Sidewalk |  |  | SY | 99 |  | 0 |  | 0 | *
Pedestrian Ramp |  |  | EA | 1190 | = | 0 |  | 0 | *
Cross Pan, local (8" thick, 6' wide to include return) |  |  | LF | 63 | = | 0 |  | 0 | *
Cross Pan, collector (9" thick, 8' wide to include return) |  |  | LF | 95 |  | 0 |  | 0 | *
Curb Chase |  |  | EA | 1532 | = | 0 |  | 0 | *
Guardrail Type 3 (W-Beam) |  |  | LF | 51 | = | 0 |  | 0 | *
Guardrail Type 7 (Concrete) |  |  | LF | 75 | = | 0 |  | 0 | *
Guardrail End Anchorage |  |  | EA | 2172 | = | 0 |  | 0 | *
Guardrail Impact Attenuator |  |  | EA | 3899 | = | 0 |  | 0 | *
Sound Barrier Fence (CMU block, 6' high) |  |  | LF | 81 |  | 0 |  | 0 | *
Sound Barrier Fence (panels, 6' high) |  |  | LF | 83 | = | 0 |  | 0
Electrical Conduit, Size = |  |  | LF | 17 | = | 0 |  | 0 | *
Traffic Signal, complete intersection |  |  | EA | 439875 | = | 0 |  | 0 | *
Traffic Signal, complete intersection |  |  | EA | 439875 | = | 0 |  | 0 | *
[insert items not listed but part of construction plans] |  |  |  |  | = | 0 |  | 0 | *
STORM DRAIN IMPROVEMENTS | [8 empty] | *
Concrete Box Culvert (M Standard), Size ( 3' x 10' ) |  | 124 | LF | 750 | = | 93000 |  | 93000 | * | Culvert across Latigo Blvd
18" Reinforced Concrete Pipe |  | 73 | LF | 67 | = | 4891 |  | 4891 | *
24" Reinforced Concrete Pipe |  |  | LF | 81 | = | 0 |  | 0 | *
34" x 53" Horizontal Elliptical Reinforced Concrete Pipe |  | 151 | LF | 150 | = | 22650 |  | 22650 | *
30" Reinforced Concrete Pipe |  | 80 | LF | 100 | = | 8000 |  | 8000 | *
36" Reinforced Concrete Pipe |  | 31 | LF | 140 |  | 4340 |  | 4340 |  | Pipe extension into Pond G18
42" Reinforced Concrete Pipe |  | 91 | LF | 166 | = | 15106 |  | 15106 | *
48" Reinforced Concrete Pipe |  | 75 | LF | 202 | = | 15150 |  | 15150 | *
54" Reinforced Concrete Pipe |  |  | LF | 254 | = | 0 |  | 0 | *
60" Reinforced Concrete Pipe |  |  | LF | 298 | = | 0 |  | 0 | *
48" x 76" HERCP |  | 79 | LF | 310 | = | 24490 |  | 24490
66" Reinforced Concrete Pipe |  |  | LF | 344 | = | 0 |  | 0 | *
72" Reinforced Concrete Pipe |  |  | LF | 393 | = | 0 |  | 0 | *
18" Corrugated Steel Pipe |  |  | LF | 87 | = | 0 |  | 0 | *
24" Corrugated Steel Pipe |  |  | LF | 99 | = | 0 |  | 0 | *
30" Corrugated Steel Pipe |  |  | LF | 126 | = | 0 |  | 0 | *
36" Corrugated Steel Pipe |  |  | LF | 152 | = | 0 |  | 0 | *
42" Corrugated Steel Pipe |  |  | LF | 174 | = | 0 |  | 0 | *
48" Corrugated Steel Pipe |  |  | LF | 184 | = | 0 |  | 0 | *
54" Corrugated Steel Pipe |  |  | LF | 269 | = | 0 |  | 0 | *
60" Corrugated Steel Pipe |  |  | LF | 290 | = | 0 |  | 0 | *
66" Corrugated Steel Pipe |  |  | LF | 352 | = | 0 |  | 0 | *
72" Corrugated Steel Pipe |  |  | LF | 414 | = | 0 |  | 0
78" Corrugated Steel Pipe |  |  | LF | 476 | = | 0 |  | 0
84" Corrugated Steel Pipe |  |  | LF | 569 | = | 0 |  | 0
18" - Flared End Section (FES) |  | 2 | EA | 402 |  | 804 |  | 804
24" - Flared End Section (FES) |  |  | EA | 486 |  | 0 |  | 0 | *
30" - Flared End Section (FES) |  | 2 | EA | 600 |  | 1200 |  | 1200 | *
Flared End Section (FES) RCP Size = (unit cost = 6x pipe unit cost) |  |  | EA |  | = | 0 |  | 0 | *
Flared End Section (FES) CSP Size = (unit cost = 6x pipe unit cost) |  |  | EA |  | = | 0 |  | 0 | *
42" - Flared End Section (FES) |  | 2 | EA | 996 |  | 1992 |  | 1992
48" - Flared End Section (FES) |  |  |  | 1212 |  | 0 |  | 0
34" x 53" - Flared End Section (FES) |  |  | EA | 600 |  | 0 |  | 0 | *
48" x 76" - Flared End Section (FES) |  |  | EA | 1500 |  | 0 |  | 0
30" HDPE Pipe |  | 64 | LF | 100 |  | 6400 |  | 6400
30" Headwall |  | 2 | EA |  |  | 0 |  | 0
34" x 53" HERCP Headwall |  | 4 | EA |  |  | 0 |  | 0
48" Headwall |  | 2 | EA |  |  | 0 |  | 0
48" x 76" Headwall |  | 2 | EA |  |  | 0 |  | 0
3' x 10' Headwall (twin) |  | 2 | EA | 10000 |  | 20000 |  | 20000
End Treatment- Headwall |  |  | EA |  | = | 0 |  | 0 | *
End Treatment- Wingwall |  |  | EA |  | = | 0 |  | 0 | *
End Treatment - Cutoff Wall |  |  | EA |  | = | 0 |  | 0 | *
Curb Inlet (Type R) L=5', Depth < 5' |  |  | EA | 5736 | = | 0 |  | 0 | *
Curb Inlet (Type R) L=5', 5' ≤ Depth < 10' |  |  | EA | 7440 | = | 0 |  | 0 | *
Curb Inlet (Type R) L =5', 10' ≤ Depth < 15' |  |  | EA | 8637 | = | 0 |  | 0 | *
Curb Inlet (Type R) L =10', Depth < 5' |  |  | EA | 7894 | = | 0 |  | 0 | *
Curb Inlet (Type R) L =10', 5' ≤ Depth < 10' |  |  | EA | 8136 | = | 0 |  | 0 | *
Curb Inlet (Type R) L =10', 10' ≤ Depth < 15' |  |  | EA | 10185 | = | 0 |  | 0 | *
Curb Inlet (Type R) L =15', Depth < 5' |  |  | EA | 10265 | = | 0 |  | 0 | *
Curb Inlet (Type R) L =15', 5' ≤ Depth < 10' |  |  | EA | 11005 | = | 0 |  | 0 | *
Curb Inlet (Type R) L =15', 10' ≤ Depth < 15' |  |  | EA | 12034 | = | 0 |  | 0 | *
Curb Inlet (Type R) L =20', Depth < 5' |  |  | EA | 10940 | = | 0 |  | 0 | *
Curb Inlet (Type R) L =20', 5' ≤ Depth < 10' |  |  | EA | 12075 | = | 0 |  | 0 | *
Grated Inlet (Type C), Depth < 5' |  |  | EA | 4802 | = | 0 |  | 0 | *
Grated Inlet (Type D), Depth < 5' |  |  | EA | 5932 | = | 0 |  | 0 | *
Storm Sewer Manhole, Box Base |  |  | EA | 12034 | = | 0 |  | 0 | *
Storm Sewer Manhole, Slab Base |  |  | EA | 6619 | = | 0 |  | 0 | *
Geotextile (Erosion Control) |  |  | SY | 6.2 | = | 0 |  | 0 | *
Rip Rap, Type L Soil |  | 600 | SY | 150 | = | 90000 |  | 90000 | *
Rip Rap, Grouted |  |  | Tons | 98 | = | 0 |  | 0 | *
Drainage Channel Construction, Size ( W x H ) |  |  | LF |  | = | 0 |  | 0
Drainage Channel Lining, Concrete |  |  | CY | 590 | = | 0 |  | 0 | *
Drainage Channel Lining, Rip Rap |  |  | CY | 116 | = | 0 |  | 0
Drainage Channel Lining, Grass |  |  | AC |  | = | 0 |  | 0
Drainage Channel Lining, Other Stabilization |  |  |  |  | = | 0 |  | 0
[5 empty] | = | 0 |  | 0
[insert items not listed but part of construction plans] |  |  |  |  | = | 0 |  | 0
* - Subject to defect warranty financial assurance. A minimum of 20% shall be retained until final acceptance (MAXIMUM OF 80% COMPLETE ALLOWED) |  | Section 2 Subtotal |  |  | = | 890061.6296 |  | 890061.6296
SECTION 3 - COMMON DEVELOPMENT IMPROVEMENTS (Private or District and NOT Maintained by EPC)**
ROADWAY IMPROVEMENTS
[5 empty] | = | 0 |  | 0
[5 empty] | = | 0 |  | 0
[5 empty] | = | 0 |  | 0
[5 empty] | = | 0 |  | 0
[5 empty] | = | 0 |  | 0
[5 empty] | = | 0 |  | 0
STORM DRAIN IMPROVEMENTS |  |  | (Exception: Permanent Pond/BMP shall be itemized under Section 1)
[5 empty] | = | 0 |  | 0
[5 empty] | = | 0 |  | 0
[5 empty] | = | 0 |  | 0
[6 empty] | 0 |  | 0
[5 empty] | = | 0 |  | 0
UTILITY SYSTEM IMPROVEMENTS
Water Main Pipe (PVC), Size 8" |  | 5800 | LF | 66 | = | 382800 |  | 382800
Water Main Pipe (PVC), Size 12" |  |  | LF | 100 |  | 0 |  | 0
Water Main Pipe (Ductile Iron), Size 8" |  |  | LF | 78 | = | 0 |  | 0
Gate Valves, 8" |  | 8 | EA | 1923 | = | 15384 |  | 15384
Gate Valves, 12" |  |  | EA | 2900 |  | 0 |  | 0
Fire Hydrant Assembly, w/ all valves |  | 11 | EA | 6828 | = | 75108 |  | 75108
Water Service Line Installation, inc. tap and valves |  | 37 | EA | 1370 | = | 50690 |  | 50690
Fire Cistern Installation, complete |  |  | EA |  | = | 0 |  | 0
Raw Water Pipe (PVC), Size 8" |  |  | LF | 66 | = | 0 |  | 0
Raw Water Gate Valves, 8" |  |  | EA | 1923 | = | 0 |  | 0
Electrical per lot |  |  | EA | 2800 | = | 0 |  | 0
Gas Main |  |  | LF | 25 | = | 0 |  | 0
Gas Service (50' per lot @$15/lf) |  |  | EA | 750 | = | 0 |  | 0
[insert items not listed but part of construction plans] |  |  |  |  | = | 0 |  | 0
SANITARY SEWER IMPROVEMENTS
Sewer Main Pipe (PVC), Size 8" |  |  | LF | 66 | = | 0 |  | 0
Sanitary Sewer Manhole, Depth < 15 feet |  |  | EA | 4540 | = | 0 |  | 0
Sanitary Service Line Installation, complete |  |  | EA | 1451 | = | 0 |  | 0
Sanitary Sewer Lift Station, complete |  |  | EA |  | = | 0 |  | 0
[5 empty] | = | 0 |  | 0
[insert items not listed but part of construction plans] |  |  |  |  | = | 0 |  | 0
LANDSCAPING IMPROVEMENTS |  |  | (For subdivision specific condition of approval, or PUD)
|  |  | EA |  | = | 0 |  | 0
|  |  | EA |  | = | 0 |  | 0
|  |  | EA |  | = | 0 |  | 0
|  |  | EA |  | = | 0 |  | 0
|  |  | EA |  | = | 0 |  | 0
** - Section 3 is not subject to defect warranty requirements |  | Section 3 Subtotal |  |  | = | 523982 |  | 523982
AS-BUILT PLANS (Public Improvements inc. Permanent WQCV BMPs) |  |  | LS | 10000 | = | 10000 |  | 10000
POND/BMP CERTIFICATION (inc. elevations and volume calculations) |  |  | LS | 10000 | = | 10000 |  | 10000
[7 empty] | Total Construction Financial Assurance | 1904422.4796
(Sum of all section subtotals plus as-builts and pond/BMP certification)
[7 empty] | Total Remaining Construction Financial Assurance (with Pre-Plat Construction) | 1904422.4796
(Sum of all section totals less credit for items complete plus as-builts and pond/BMP certification)
[7 empty] | Total Defect Warranty Financial Assurance | 220062.0659
(20% of all items identified as (*). To be collateralized at time of preliminary acceptance)
Approvals
I hereby certify that this is an accurate and complete estimate of costs for the work as shown on the Grading and Erosion Control Plan and Construction Drawings associated with the Project.
Engineer (P.E. Seal Required)
Approved by Owner / Applicant |  |  |  | Date
Approved by El Paso County Engineer / ECM Administrator |  |  |  | Date