# TANNER RANCH FILING NO. 1

# THIRD AMENDED AND RESTATED

# SUBDIVISION IMPROVEMENTS AGREEMENT

THIS THIRD AMENDED AND RESTATED SUBDIVISION IMPROVEMENTS AGREEMENT, made between Pusan Holdings, LLC, hereinafter called the "Subdivider," and El Paso County by and through the Board of County Commissioners of El Paso County, Colorado, hereinafter called the "County," is entered into and effective this ____ day of _____, 2026 (“Effective Date”).

WHEREAS, Tanner Ranch, LLC, the “Previous Developer,” as a condition of approval of the final plat for the Tanner Ranch Filing No. 1 subdivision (“Subdivision”), entered into a Subdivision Improvements Agreement (“SIA”) as provided for by Section 30-28-137 (C.R.S.), Chapter 5 of the El Paso County Engineering Criteria Manual and Chapter 8 of the El Paso County Land Development Code, which SIA was recorded in the records of the El Paso County Clerk and Recorder on May 5, 2006 at Reception No. 206067989; and

WHEREAS, the County subsequently approved an amendment to the SIA which substituted a restriction upon the sale of lots within the Subdivision for a performance bond in order to secure performance of Subdivider’s obligations (“Amended SIA”), which Amended SIA was recorded in the records of the El Paso County Clerk and Recorder on April 16, 2012 at Reception No. 212042951; and

WHEREAS, the County and Previous Developer subsequently entered into an Amended and Restated Subdivision Improvements Agreement (“Restated SIA”) on March 12, 2015, adopting a phased approach to the construction of public improvements and the provision of sufficient collateral, which Restated SIA was recorded in the records of the El Paso Clerk and Recorder on April 20, 2016 at Reception No. 215037502; and

WHEREAS, the County and Previous Developer entered into a Letter Agreement to Extend Amended and Restated Subdivision Improvements Agreement (“Letter Agreement”) on April 22, 2020 extending the deadline to complete the public improvements for the Subdivision and imposing more specific conditions on the Subdivider in connection therewith; and

WHEREAS, the County and Previous Developer entered into an Amended Letter Agreement to Extend Amended and Restated Subdivision Improvements Agreement (“Amended Letter Agreement”), approved on November 3, 2020 pursuant to Resolution No. 20-374, again extending the deadline to complete the public improvements for the Subdivision to December 15, 2020 and granting the authority grant an additional 3-month extension to the El Paso County ECM Administrator, which extension was granted until March 15, 2021; and

WHEREAS, the County and Previous Developer entered into an Amendment to Subdivision Improvements Agreement (“Amendment”), approved on March 16, 2021 pursuant to Resolution No. 21-97, which extended the terms and provisions of the Restated SIA, Letter Agreement, and Amended Letter Agreement to April 25, 2021; and

WHEREAS, most recently, the County and Previous Developer entered into a Second Amended and Restated Subdivision Improvements Agreement (“Second Agreement”), approved on April 13, 2021 pursuant to Resolution No. 21-139; and

WHEREAS, a purchase of the Subdivision is pending, and the County and Subdivider wish to enter into this Third Amended and Restated Subdivision Improvements Agreement to provide for the replacement of the current collateral and eliminate the need for phasing the remaining public improvements.

NOW, THEREFORE, in consideration of the following mutual covenants and agreements, the Subdivider and the County agree as follows:

1.	This Third Amended and Restated Subdivision Improvements Agreement (“Third Agreement”) supersedes and replaces the SIA, the Amended SIA, the Restated SIA, the Letter Agreement, the Amended Letter Agreement, the Amendment, and the Second Agreement.  The Parties agree that all of those prior agreements are hereby terminated.

2.	The Subdivider agrees to construct and install, at his sole expense, all of those improvements as set forth in Exhibit A, attached hereto and incorporated herein by reference.  To secure and guarantee performance of its obligations as set forth herein, the Subdivider agrees to provide collateral to remain in effect at all times until the improvements are completed and accepted in accordance with Chapter 5 of the El Paso County Engineering Criteria Manual (“ECM”). Collateral shall be posted in the form of an irrevocable letter of credit issued by ____________(Bank)____________________or by a surety bond in the amount of $_________.

- Upon recording of this Third Agreement and posting of collateral, the Subdivider may sell Lots 1 and 2 to Tri County Fire Department for the purpose of construction of a new fire station. All infrastructure required to be built for access shall be the responsibility of the Subdivider.

- Applications for building permits for Lots 10, 11, 26, 27, 30, 32, 34 – 46 may be submitted once all of the following have occurred: i) posting the collateral described above; ii) granting an easement, in a form acceptable to the County, along the portion of Dinner Bell Drive from the boundary of the Subdivision to Calhan Highway; and iii) construction of the portion of Dinner Bell Drive from the boundary of the Subdivision to Calhan Highway in accordance with approved construction plans, up to and including the base course but not including paving. The driving surface may be 24’ wide with written approval of the Tri County Fire Department.

3.  	To secure and guarantee performance of its obligations as set forth herein, the Subdivider agrees to provide collateral to remain in effect at all times until the improvements are completed and accepted in accordance with Chapter 5 of the ECM.  Subdivider is responsible for providing any renewals of collateral to ensure that there is never a lapse in coverage.  Subdivider shall procure renewal/extension/replacement collateral at least fifteen (15) days prior to the expiration of the collateral then in effect.  Failure to procure renewal/extension/replacement collateral within this time limit shall be a default under this Agreement and shall allow the County to execute on the collateral.  In addition, if Subdivider allows collateral to lapse at any time, no lots in the subdivision may be sold, conveyed or transferred, whether by Deed or Contract, after the expiration date of such collateral until the improvements identified on Exhibit A have been completed and final acceptance is received from the County.  If replacement collateral is used for renewal, approval by Board of County Commissioners is required.

4.	No lots in the subdivision shall be sold, conveyed or transferred, whether by Deed or by Contract, nor shall building permits be issued until and unless the required improvements for the subdivision have been constructed and completed in accordance with the approved construction plans and preliminary acceptance is received from the County.  In the alternative, lots within the subdivision may be sold, conveyed or transferred and / or have building permits issued in accordance with the provisions set forth in paragraph 2 above.

5.	The Subdivider agrees that all of those certain public improvements to be completed as identified on Exhibit A shall be constructed in compliance with the following:

a.	All laws, resolutions and regulations of the United States, State of Colorado, El Paso County and its various agencies, affected special districts and/or servicing authorities.

b.	Such other designs, drawings, maps, specifications, sketches and other matter submitted to and approved by any of the above-stated governmental entities.

6.	All improvements shall be completed by the Subdivider, meeting all applicable standards for preliminary acceptance, within 24 (twenty-four) months from the date of notice to proceed in the Construction Permit for the Subdivision.  If the Subdivider determines that the completion date needs to be extended, the Subdivider shall submit a written request for a change in the completion date to the ECM Administrator at least 90 days in advance of the required completion date. The request shall include the reasons for the requested change in completion date, the proposed new completion date, and prove collateral is in place to cover the extension time requested. The completion date for the Subdivision may be extended one time, in writing and for a period no longer than 12 months, at the discretion of the ECM Administrator. A second extension of the completion date for a period of no longer than 12 months may be considered and approved, in writing, at the discretion of the Department of Public Works (DPW) Director.  Any additional requests for extension of the completion date will be scheduled for hearing by the Board of County Commissioners. The ECM Administrator, DPW Director, or the Board of County Commissioners may require an adjustment in the amount of collateral to take into account any increase in cost due to the delay including inflation.

7.	It is mutually agreed pursuant to the provisions of Section 30-28-l37 (3) C.R.S. that the County or any purchaser of any lot, lots, tract or tracts of land subject to a plat restriction which is the security portion of a Subdivision Improvements Agreement shall have the authority to bring an action in any District Court to compel the enforcement of any Subdivision Improvements Agreement on the sale, conveyance, or transfer of any such lot, lots, tract or tracts of land or of any other provision of this article.  Such authority shall include the right to compel rescission of any sale, conveyance, or transfer of any lot, lots, tract or tracts of land contrary to the provisions of any such restrictions set forth on the plat or in any separate recorded instrument, but any such action shall be commenced prior to the issuance of a building permit by the County where so required or otherwise prior to commencement of construction on any such lot, lots, tract or tracts of land.

8.	It is further mutually agreed that, pursuant to the provisions of Section 30-28-l37 (2) C.R.S., and Chapter 5 of the County’s Engineering Criteria Manual, as improvements are completed, the Subdivider may apply to the Board of County Commissioners for a release of part or all of the collateral deposited with said Board.  Upon inspection and approval, the Board shall release said collateral.  If the Board determines that any of such improvements are not constructed in substantial compliance with specifications it shall furnish the Subdivider a list of specific deficiencies and shall be entitled to withhold collateral sufficient to ensure such substantial compliance.  If the Board of County Commissioners determines that the Subdivider will not construct any or all of the improvements in accordance with all of the specifications, the Board of County Commissioners may withdraw and employ from the deposit of collateral such funds as may be necessary to construct the improvements in accordance with the specifications.

9.	The Subdivider agrees and both parties acknowledge that the construction of the improvements identified and guaranteed through this Subdivision Improvements Agreement shall follow the inspection, collateral, and acceptance process identified in Chapter 5 of the County’s Engineering Criteria Manual. This is to include, among other things, a Preliminary Acceptance process, replacement of performance collateral with appropriate Warranty collateral at that time, and a 2-year warranty period prior to final acceptance. Where any inconsistency exists between Chapter 5 of the Engineering Criteria Manual and the Land Development Code with respect to these inspection, collateral and acceptance processes, the Engineering Criteria Manual is the controlling document.

10.	Parties hereto mutually agree that this Agreement may be amended from time to time provided that such amendment be in writing and signed by all parties hereto.

IN WITNESS WHEREOF, the parties have hereunto set their hands and seals the day and year below written.

# BOARD OF COUNTY COMMISSIONERS OF

# ATTEST:					EL PASO COUNTY, COLORADO

_________________________________	By: _____________________________________

Chuck Broerman                                            		 Carrie Geitner, Chair

County Clerk and Recorder

Approved as to form:

__________________________________

County Attorney’s Office

SUBDIVIDER:

PUSAN HOLDINGS, LLC

By: ________________________________

(signature)

_____________________________

(Printed name)

Its: ________________________________

(Title)

Subscribed, sworn to and acknowledged before me this _______ day of _____________, 2026, by ______________________________, as _________________________ of Pusan Holdings, LLC.

# My commission expires: ____________________.

____________________________________________

Notary Public