Trails at Aspen Repairs 2025

June 9th Ironex moved in their equipment.

June 10th Ironex started their excavation on between 7865 and 7853 Buffalo Horn. Ironex excavated to the sewer pipe.

June 11th Ironex exposed the sewer pipe found where it was damaged and did a replacement. They then back filled around the sewer pipe with 57/67 rock material to protect the sewer pipe. After about 3ft of 57/67 material they then started to back fill it with the dirt materials, doing 2ft lifts then having it tested by CMT.

June 12th Ironex completes back fill with dirt materials and finishes topping off the last 5ft with road base.

June 13th Ironex only worked till about noon to with making their next street cut. And opening it up.

June 16th Ironex excavated down to sewer pipe.

June 17th Ironex exposed the rest of the sewer pipe found the broken piece and did a repair. As Ironex was doing the repair we did get a lot of rain that ended filling the hole up about 4ft of water.

June 18th Ironex had to pump out all the water from the opening. After finishing with pumping out all the water they finished repairing the sewer pipe as well as making it a little more level. Ironex, they started to back fill with the 57/67 materials to protect the sewer pipe. They went up about 4ft of the 57/67.

June 19th Ironex has been struggling with trying to get the boxes out of the hole so they could back fill. The boxes are stuck in the hole due to all the native dirt that has collapsed around it with all the rain we got the previous day.

June 20th Ironex finished back filling the hole and only worked a half day.

June 23rd Ironex started to open another hole on the intersection of Buffalo Horn and Lazy Ridge.

June 24th Ironex dig down about halfway to pipe. Took them a little longer to dig with gas drainage electric and water all in this section.

June 25th Ironex has finished digging to the sewer pipe. They have a lot of ground water coming from it. I have not seen CMT out on site for the last 2 days. Ironex will be getting ready to fix sewer.

June 26th Ironex has started to pump out more water this morning. They are also down in the manhole breaking some concrete so they can try to raise the sewer pipe. Ironex finally got the sewer pipe uncovered enough to raise the pipe about 4 inches it is now where it should be, and they are putting 57/67 rock under the pipe to keep it from falling again. Starting tomorrow they should be starting to back fill.

Digging is going slow Ironex is trying to make progress. They do have another crew that is going ahead of them to pothole for them to find the lines. Ironex has hit 2 gas lines within 3 weeks of each other. So that has slowed them down a little bit. Dew to hitting the gas lines they did change up things a little with always having a spotter while digging.

August 26th through the 29th Ironex did not do any digging due to all the rain we are having. The crew was out there doing some clean up with all the mud. Site in good condition.

September 10th  Ironex is continuing to dig and are moving along pretty good. They are making sure they have spotters still so they do not hit any more gas lines. They are doing an amazing job with making sure they are tamping the dirt.

September 11th Ironex opened another whole. Site is in good condition.

September 12th Ironex is just doing a small hole today they will be done working by 1 today.

September 16th Pyrmid is now on the top end of buffalo horn and is starting to break out the sidewalk the needs to be repaired.  When they get everything done we will be doing a proof roll before they start putting in forms.

September 17th Pyrmid is still working on pulling out some of the dirt so they can make it to grade. They will be working on the rest of the week and will still to pour next week.

September 19th I got a call from the Gage with cmt saying that pyrmid has poured some sidewalk. When I got there they was almost done and I talked to the guy that was doing the concrete work and told him that it all had to come out because we did not get passing tests on any of this. He called his boss said that they had to take it out. They did not take it out I did let David know that they poured and he met me out there he did take pictures and he did call Ronin and tell him that it had to come out. Come Tuesday they still did not take it out I did put more pink xes on it so that why it was marked and they knew it was coming out.

September 23rd Did a proof roll for Pyrmid for curb and gutter. Everything passes on one side but not the other. After poof roll they put up the forms so they could pour tomorrow.

September 24th Concrete pour was at 10 this morning. Concrete passes and then we did another proof roll for the other side so they could set forms up. Proof roll went good other than one spot they will let the one curb and gutter dry out for the next couple days and they we will proof roll that again.