## V3_Financial Assurance Forms_
Comments | Author | Date | Status
change to 78,597.41 to match FDR. Retotal sheet | eschoenheit | 2026-03-25 13:43 | Accepted set by milos on 4/1/2026 at 3:24:03 PM
Updated to match FDR. | milos | 2026-04-01 15:24

## V3_Letter of Intent_
Comments | Author | Date | Status
PCD number: PPR2527 | Jalal Saleh | 2026-03-25 09:52 | Accepted set by milos on 4/1/2026 at 5:03:02 PM
PCD number now included. | milos | 2026-04-01 17:03
5.2.40 Outside Storage | marialancto | 2026-03-26 12:10 | Accepted set by milos on 4/1/2026 at 5:03:58 PM
Added 5.2.40 discussion here. | milos | 2026-04-01 17:04
This is all good information, so please keep it in some capacity, but it does not match the referenced code section. I'll follow up with an email with code sec. 5.2.40 which has the criteria for outdoor storage. Please use this section to describe how each of the criteria are met with this proposal. The information here can be moved out of this section and into its own section/paragraph. | marialancto | 2026-03-26 12:08 | Accepted set by milos on 4/1/2026 at 5:05:04 PM
The discussion now matches the referenced section and the general information is moved to a "general criteria" section on page 4. | milos | 2026-04-01 17:05
Section 5.2.50(B) is not variance of use criteria - its is shipping containers in residential zone districts. I'll follow up withe the code section. The information currently in this section can be removed entirely as the variance of use has already been approved and is therefore not evaluated with this application. Please use this section to address the criteria of 5.2.50(B). | marialancto | 2026-03-26 12:10 | Accepted set by milos on 4/1/2026 at 5:05:50 PM
Variance of use discussion is removed and replaced with section 5.2.50(B) discussion. | milos | 2026-04-01 17:06
| marialancto | 2026-03-26 12:10
good - thanks for including this | marialancto | 2026-03-26 12:12 | Accepted set by milos on 4/1/2026 at 5:05:57 PM

## V3_Drainage Report - Final_
Page Label | Comments | Author | Date | Status
13 | Please add a statement in this section similar to the following: "Refer to Appendix J for the water quality summary table, where treatment or exclusion of all basins is documented." | EPC Stormwater- Zachary | 2026-03-25 17:33 | Accepted set by milos on 4/1/2026 at 3:37:08 PM
13 | Added statement on page 14. | milos | 2026-04-01 15:37
17 | Include description and analysis for IAN2 if being used to provide permanent water quality treatment. | EPC Stormwater- Zachary | 2026-03-25 14:57 | Accepted set by milos on 4/3/2026 at 1:16:14 AM
17 | Included description and analysis for IAN2 on page 20 | milos | 2026-04-03 01:16
18 | Recommended to confirm with CDWR that this stormwater detention approach will not violate water rights. The state typically does not allow infiltration of major storms when sites have historically discharged, but since the gabion basket calculations show that flows are returned to historic it may be acceptable. This is not an EPC Stormwater requirement but it may be best to confirm the design is acceptable with the state now to avoid future issues. Attached is correspondence from the state from a different project (PCD File no MS227) for reference. No action or additional documentation is required to resolve this comment, this is just for your information. | EPC Stormwater- Zachary | 2026-03-26 08:21 | Accepted set by milos on 4/1/2026 at 3:38:15 PM
18 | The state has responded that they will not require any additional documentation and accept the infiltration basins. | milos | 2026-04-01 15:40
18 |  | EPC Stormwater- Zachary | 2026-03-26 08:21
48 | 4,467.61 sf | EPC Stormwater- Zachary | 2026-03-24 16:26
48 |  | EPC Stormwater- Zachary | 2026-03-25 13:32
48 |  | EPC Stormwater- Zachary | 2026-03-25 13:32
48 | Include these disturbed areas in the WQ treatment summary table. | EPC Stormwater- Zachary | 2026-03-26 08:32 | Accepted set by milos on 4/1/2026 at 3:40:49 PM
48 | Included all area within limits in the summary table. | milos | 2026-04-01 15:41
48 |  | EPC Stormwater- Zachary | 2026-03-26 08:32
61 | Unresolved comment from previous review: There are proposed grading contours is these basins. Please provide the area disturbed, and what exclusion is being used. | EPC Stormwater- Zachary | 2026-03-26 08:37 | Accepted set by milos on 4/1/2026 at 3:41:14 PM
61 | All disturbed areas are now shown on the table. | milos | 2026-04-01 15:41
61 | To clarify, water quality is required for all disturbance, not just development. Everything within the limits of disturbance needs to be treated or excluded, see the EPC ECM Appendix I.7.1.B and I.7.1.C for exclusions. | EPC Stormwater- Zachary | 2026-03-26 08:37 | Accepted set by milos on 4/1/2026 at 3:41:50 PM
61 | Exclusions are now shown on the table per EPC ECM Appendix 1.7.1.B.7 | milos | 2026-04-01 15:42
5 |  | eschoenheit | 2026-03-25 16:07 | Accepted set by milos on 4/1/2026 at 3:33:14 PM
5 | Add item 11 and indicate NO "Basin Fees" nor "Bridge Fees" are applicable because you are "NOT plating". | Jalal Saleh | 2026-03-25 10:47 | Completed set by milos on 4/1/2026 at 3:33:37 PM
5 | Resolved | milos | 2026-04-01 15:34
65 | This total must be shown on Section 1 subtotal of the completed FAE. | Jalal Saleh | 2026-03-25 11:03 | Accepted set by milos on 4/1/2026 at 3:34:03 PM
65 | FAE is updated. | milos | 2026-04-01 15:34

## V3_SDI Form or MHFD Detention C
Page Label | Comments | Author | Date | Status
1 | Please include an SDI sheet for IAN2 as well | EPC Stormwater- Zachary | 2026-03-24 17:08 | Accepted set by milos on 4/2/2026 at 10:15:31 PM
1 | SDI for IAN2 is now included. | milos | 2026-04-02 22:15
5 | Move all MHFD SCM Design sheets to the Drainage Report appendices | EPC Stormwater- Zachary | 2026-03-25 17:00
7 | Runoff Runoff Runoff | EPC Stormwater- Zachary | 2026-03-24 15:35 | Accepted set by milos on 4/2/2026 at 11:22:04 PM
7 | Should be WQCV design standard since they are designed to detain flows | EPC Stormwater- Zachary | 2026-03-25 09:14 | Accepted set by milos on 4/2/2026 at 10:16:30 PM
7 | Changed to WQCV | milos | 2026-04-02 22:16
7 | 0% | EPC Stormwater- Zachary | 2026-03-26 09:01
7 | 0% | EPC Stormwater- Zachary | 2026-03-26 09:01
7 | Should be at least 60% | EPC Stormwater- Zachary | 2026-03-26 09:01 | Rejected set by milos on 4/2/2026 at 11:19:13 PM
7 | The way MHFD built this sheet is that this only shows the percentage treated by RPA where an IA flows through a RPA upstream of the SCM (before entering the SCM). This also shows treatment through landscaped areas. Since no runoff reduction is being shown upstream of the SCM due to the SCMs being able to provide full treatment by themselves. Due to this, these will show 0%. The important thing to look for is the Design WQCV of the SCM and the Untreated WQCV rows below. These rows show the total result accounting for both the Runoff Reduction and sheet flow (percentage value) and the SCM treatment. As can be seen in the table, the Design WQCV of the SCM is much larger than the Default WQCV (required treatment) and the Untreated WQCV row shows 0s indicating full treatment and compliance. | milos | 2026-04-02 23:19
9 |  | EPC Stormwater- Zachary | 2026-03-26 09:05 | Rejected set by milos on 4/2/2026 at 11:20:12 PM
9 | Due to length of flow path please design for concentrated flows at pond inflow | EPC Stormwater- Zachary | 2026-03-26 09:06 | Rejected set by milos on 4/2/2026 at 10:29:52 PM
9 | It is true that for the rational method, the length from the furthest part would be considered as concentrated flow, and it is taken into account as concentrated for TOC calcs for the rational method. However, when designing for water quality and infiltration basins, engineering judgment must be used to design properly for actual site conditions. The flow into the pond is spread so wide that it will not be concentrated in reality and will have uniform sheet flow into the pond from all directions. The longest distance that you are referring too comes from a portion of the sub-basin that is very slim and small in area, whose flows will be very small and will blend with the rest of the sheet flow. | milos | 2026-04-02 22:29
10 | Please revise to recommended depth. It does not look like 28 inches is required for the WQCV. | EPC Stormwater- Zachary | 2026-03-24 15:55 | Accepted set by milos on 4/2/2026 at 10:31:50 PM
10 | Corrected. | milos | 2026-04-02 22:32
10 | Plans show bottom is flat | EPC Stormwater- Zachary | 2026-03-24 15:52 | Accepted set by milos on 4/2/2026 at 10:31:32 PM
10 | Corrected to 0 slope. | milos | 2026-04-02 22:31
14 | Surface is graveled, edger cannot be used. Choose another inflow feature or justify why none are needed. Concerned about gravel being frequently deposited into the pond. | EPC Stormwater- Zachary | 2026-03-26 09:15 | Accepted set by milos on 4/2/2026 at 10:43:31 PM
14 | None are needed, the spread flows will not displace gravel | milos | 2026-04-02 22:43
15 | Please revise to recommended depth. It does not look like 18 inches is required for the WQCV. | EPC Stormwater- Zachary | 2026-03-24 16:07 | Accepted set by milos on 4/2/2026 at 10:45:04 PM
15 | Corrected | milos | 2026-04-02 22:45
15 | Bottom is flat in plans | EPC Stormwater- Zachary | 2026-03-24 16:11 | Accepted set by milos on 4/2/2026 at 10:45:23 PM
15 | Set to 0 slope | milos | 2026-04-02 22:45
23 | Note: runoff reduction for this basin is not required as an official PCM if IAN2 provides full treatment for full WQCV (which is what the calcs show). So either choose IAN2 or runoff reduction as the official treatment method, and either remove mention of the other method or make clear that it is additional treatment not required by EPC. If runoff reduction is the chosen method the PCM Applicability Form and Detention Maintenance Agreement will need to be modified and an O&M for the buffer/swale will be required. | EPC Stormwater- Zachary | 2026-03-26 09:19 | Accepted set by milos on 4/2/2026 at 10:54:22 PM
23 | The site is designed with the advantages of Runoff reduction being present to further reduce and treat flows. For simplification, we agree with you and will remove the runoff reduction from here since IAN2 provides full treatment. | milos | 2026-04-02 22:54
25 | Does this include the concrete pad and gravel area in basin A? Measured area is ~4500 sq ft | EPC Stormwater- Zachary | 2026-03-24 16:28 | Accepted set by milos on 4/2/2026 at 11:01:02 PM
25 | Corrected to correct area. | milos | 2026-04-02 23:01
25 | Also this area may be able to be excluded per EPC ECM Appendix I.7.1.C.1.a where 20% up to 1 acre of the applicable development area (LOD) may be excluded if using the WQCV design standard | EPC Stormwater- Zachary | 2026-03-25 17:08 | Accepted set by milos on 4/2/2026 at 11:21:39 PM
25 | You are correct that it can be excluded, but we have enough capacity and treatment with our SCMs and drainage design that there is no need for utilizing the reduction as of now. | milos | 2026-04-02 23:22