Pre-Construction Meeting Package

Project Name

EDARP File #

CON #

ESQCP #

Table of Contents

Required Documents and Fees	2

PCD Quick Tips – Collateral	3

Construction Permit	5

Public Improvement Testing Requirements	6

Pavement Design Reports	10

Work in the Right-of-Way	12

Stormwater and Erosion Control	15

# Required Documents and Fees

- Construction Permit fee of $xxxx.xx

Please see link to El Paso County Fee Schedule. Select 2025 Fee Schedule under General Fees to access table and footnotes: https://planningdevelopment.elpasoco.com/#1515613078895-69552b09-44a4

Please note we will no longer accept checks in the field. This must be paid in person at Pikes Peak Regional Office prior to Notice to Proceed (2880 International Circle, Suite 110, Colorado Springs, CO 80910) OR online via EDARP.

- Surety in the amount of $xxxxxxx, in the form of an LOC, Bond, or Check with W9. The LOC and Bond forms can be found here: https://planningdevelopment.elpasoco.com/planning-development-forms/#1516906638016-61792baf-6cf4

Please note, the surety must be delivered to Pikes Peak Regional Office prior to Notice to Proceed (2880 International Circle, Suite 110, Colorado Springs, CO 80910). Please see pages 3-4 for more information on Collateral/Surety.

- CDPHE Stormwater Discharge Permit (Needed for 1 acre or more of disturbance or if the development is part of a larger common plan of development). https://ceos.colorado.gov/CO/CEOS/Public/Client/CO_CIMPLE/Shared/Pages/Main/Login.aspx

  - Once you get this permit you can install your stormwater control measures prior to the Pre-Con or Notice to Proceed (NTP) as they will need to be inspected to receive the NTP.

- El Paso County Health Department Construction Activity Permit (Needed for 1 to 25 acres of disturbance) (Valid for 6 months after approval- must renew until all earthwork is stable). https://www.elpasocountyhealth.org/licenses-permits-inspections-water-testing/air-quality/

- CDPHE Air Pollutant Emissions Notice (“APEN”) Permit (Needed for 25+ acres of disturbance) https://ceos.colorado.gov/CO/CEOS/Public/Client/CO_CIMPLE/Shared/Pages/Main/Login.aspx

Additional Items that may be Required:

- Dewatering Permit (only needed if groundwater is being pumped to the storm sewer system)

- U.S. Army Corps of Engineers (USACE) 404 Permit (for work in waterways of the state)

PCD QUICK TIPS – COLLATERAL

Collateral is posted to guarantee completion of required improvements associated with certain land use applications. These include, but are not limited to, grading and erosion control, subdivision improvements, landscaping of public and/or common improvements, defect warranty, construction removal, etc.

***Please note collateral will not be accepted without the required documents, if the amount of the collateral is incorrect, or if the collateral is not the original document. Additionally, collateral will not be accepted in the field.

Accepted Forms of Collateral

Bonds from insurance companies

Letters of Credit (LOC) from Banks and Credit Unions

Business Checks/Cashier’s Check from Banks

Requirements

All forms of accepted collateral must be from a Bank, Credit Union, or Insurance Company registered and in good standing to do business in the State of Colorado.

An approved Financial Assurance Estimate (FAE) is required for all bonds, LOCs, and checks (not applicable for escrow).

A copy of the construction permit is required when submitting collateral. The collateral amount must match the posted amount listed on the construction permit.

An updated and complete W-9 form is required with all checks for collateral and escrow. The W-9 must match the company/individual name listed on the check.

If submitting 100% of the collateral prior to the recording of the Final Plat, an approved FAE, and recorded SIA are required.

If submitting collateral for pre-subdivision site grading only, section one of the approved FAE is to be provided along with a signed Pre-Subdivision Site Grading Acknowledgement and Right of Access form.

If collateral is required at the time of site development plan approval, an approved FAE, and construction permit are required. A Development Agreement may be required if indicated on the construction permit.

ESCROW: Checks are the only acceptable form of payment when submitting an escrow and no other fees may be included in a check for escrow. A signed escrow agreement must accompany the check, and the check amount must match the amount in the agreement.

Releases

Releases or reductions of collateral are done at the time of Preliminary Acceptance (PA) and Final Acceptance (FA). There may be up to three reductions during construction prior to a PA. For PAs, the assigned engineer must submit an FAE with the % Complete column completed. Please note that anything with a red asterisk cannot have more than an 80% release.

Resources

For additional information call us at 719-520-6300 or for questions specifically regarding inspections or pre-construction meetings, contact us at: dpw-dsinspections@elpasoco.com.

You may also view collateral related documents online at planningdevelopment.elpasoco.com. Select the Forms, Applications, and Checklists tab to see Collateral/Surety information and documents.

Collateral is to be delivered or mailed to:

Planning and Community Development

2880 International Circle, Suite 110

Colorado Springs, CO 80910

*Please note that collateral will not be accepted and will be mailed back if the required documents are not included.

Department of Public Works | Development Services

Construction Permit: (Project Name) File Number: (EDARP File Numbers)

Total Amount of the FAE: (amount of the approved FAE)			Inspector:

Posted Amount of the FAE: (Amount posted)	Section 1 		Review Engineer:

Date Received: _________ Type of Surety: LOC  Bond 	Check 	W9 	Accepted By: __________________________________

SIA 	Required		Not Required 				Dev Agreement	Required		Not Required

Name of Development/Subdivision: (EDARP project name)

Location of Construction: (subdivision or address)

Description of Construction / Fee: (fee type)

Construction permit fee (insert permit fee here)

Date of Plan Approval and / or Dev. Agreement: (date)

Responsible Person/Company: (name)

Responsible Party Street Address (address)

Responsible Party City / State / Zip (city/state/zip code)

Responsible Party Phone / Email (email)

Land Development Code and Engineering Criteria Manual Compliance Guideline Checklist:

Preliminary Plan Approval Early Grading  or  	Development / Subdivision Construction Plan

Preliminary Drainage Report Approval      or  	Final Drainage Letter / Report

All County permits obtained

(may include but not limited to Construction Activity, ESQCP, Grading, Access, etc.)

Copies of Other Agency / Entity Permits

(may include but not limited to Colorado Discharge, Corp of Engineers, Floodplain,

Endangered Species, US Fish and Wildlife, etc.)

Initial BMP inspection. Must be completed by the Stormwater team before any work on the site can be performed.

Pre-construction Meeting

Pavement Design Required

This is to advise that the person or company responsible for construction of all public and common development improvements, as authorized by this Construction Permit and in accordance with the above referenced development or subdivision improvements agreement agrees to construct the required improvements in full conformance of all County rules, regulations, codes, standards, and ordinances, approved plans, applicable development or subdivision improvements agreement, and development permits or approvals. It is understood and agreed that, upon completion of construction and at the time of any request for release of surety, preliminary or final acceptance, the project's  engineer shall certify that the work has been entirely completed, and that it conforms in all respects, with all County rules, regulations, codes, standards, and ordinances, approved plans, applicable development or subdivision improvements agreement, and development permits or approvals; and to all specifications required by the laws and regulations of the State of Colorado.

___________________________________________

Applicant signature

______________________________

County Representative signature

Notice-to-Proceed is given on this day ______________ Permit Expires: _________________

Install initial stormwater control measures and call for inspection prior to any additional land disturbance.

# Public Improvement Testing Requirements

Requirements:

- Add DPW to the distribution list for all testing reports, in a timely fashion, necessary to comply with the ECM Standards.  A summary sheet of typical requirements is included with this document.

- Minimum testing intervals of 250 LF applicable to trenches, 250 Lane Ft. subgrade.

- Testing of trenches / embankments not to exceed 2-foot depth intervals.

- Provide pavement design along with HBP mix design to DPW for review / approval at least 10 working days prior to anticipated date of placement.

- Contact DPW for subgrade inspection / proof roll prior to placement of gravel or pavement.

Signing and Striping Notes:

1. All signs and pavement markings shall be in compliance with the current Manual on Uniform Traffic Control Devices (MUTCD).

2. Removal of existing pavement markings shall be accomplished by a method that does not materially damage the pavement. The pavement markings shall be removed to the extent that they will not be visible under day or night conditions. At no time will it be acceptable to paint over existing pavement markings.

3. Any deviation from the striping and signing plan shall be approved by El Paso County Department of Public Works (DPW).

4. All signs shown on the signing and striping plan shall be new signs. Existing signs may remain or be reused if they meet current El Paso County and MUTCD standards.

5. Street name and regulatory stop signs shall be on the same post at intersections.

6. All removed signs shall be disposed of in a proper manner by the contractor.

7. All street name signs shall have “D” series letters, with local roadway signs being 4” upper-lower case lettering on 8” blank and non-local roadway signs being 6” letting, upper-lower case on 12” blank, with a white border that is not recessed. Multi-lane roadways with speed limits of 35 mph or higher shall have 8” upper-lower case lettering on 12” blank with a white border that is not recessed. The width of the non-recessed white borders shall match page 255 of the FHWA Standard Highway Signs: 2004 Edition with 2012 Supplement. Signal pole mounted and overhead street name signs shall be per MUTCD size standards.

8. All traffic signs shall have a minimum diamond grade retroreflective sheeting that meets ASTM D4956 Type XI sheeting requirements.

9. All local residential street signs shall be mounted on a 1.75” x 1.75” square tube post and stub post base. For other applications, refer to the CDOT Standard S-614-8 regarding use of the P2 tubular steel post slipbase design.

10. All signs shall be single sheet aluminum with 0.125” minimum thickness.

11. All limit lines/stop lines, crosswalk lines, pavement legends, and arrows shall be a minimum 125 mil thickness preformed thermoplastic pavement markings with tapered leading edges per CDOT Standard S-627-1. Stop bars shall be 24” in width. Crosswalks lines shall be 24” in width and a minimum of 9’ long. Crosswalks shall be inlaid in accordance with Section 627 of the 2025 CDOT Standard Specification for Road and Bridge Construction.

12. Word and symbol markings shall be the narrow type.

13. All longitudinal lines shall be a minimum 18 mil thickness epoxy paint. All non-local residential roadways shall include both right and left edge line striping and any additional striping as required by CDOT S-627-1.

14. All signs shall be placed in accordance with CDOT Standard S-614-1 or MUTCD Figure 2A-2.

15. The contractor shall notify El Paso County DPW - Inspections (719) 520-6819 prior to and upon completion of signing and striping.

16. The contractor shall obtain a work in the right of way permit from the El Paso County DPW prior to any signage or striping work within an existing El Paso County roadway.

J.5. - TESTING SUMMARY

Table J-3 summarizes the testing requirements outlined in Appendix J.

Table J-3. Summary Minimum Testing Requirements

| No. | Item | Type Of Test | Minimum Frequency | Min. # | Act. # |
| --- | --- | --- | --- | --- | --- |
| 1 | Utilities: Water, Sewer, Gas, Electric, Phone and Cable Trenches | Moisture/Density | 1 per every 250 L.F. or fraction thereof, every 2' elevation. Each structure (manhole, valve, etc.) every 2' elevations. This requirement also applies to every service. |  |  |
| 2 | Storm Sewer Trench | Moisture/Density | Same as above. Each structure (manhole, inlet, etc.) every 2' elevations. |  |  |
| 3 | Inlets Concrete Testing | Air Slump | First load or until compliance. Minimum 1 per day. |  |  |
|  |  | Cylinders | 1 set (4) per project for every 100 C.Y. or fraction thereof. |  |  |
|  |  | Steel | Visual and Documentation |  |  |
| 4 | Curb and Gutter | Moisture/Density | 1 every 250 feet or a minimum of 3 tests, whichever is greater. |  |  |
|  |  | Proof-Roll | All final subgrade. |  |  |
|  |  | Air/Slump | First load or until compliance. Minimum 1 per every 2,000 L.F. or fraction thereof. |  |  |
|  |  | Cylinders | 1 set (4) per project every 2,000 L.F. or fraction thereof. |  |  |
| 5 | Sidewalk | Moisture/Density | 1 per every 250 L.F. or fraction thereof. |  |  |
|  |  | Air/Slump | First load or until compliance. Minimum 1 per every 1,000 S.Y. or fraction thereof. |  |  |
|  |  | Cylinders | 1 set (4) per project 1,000 S.Y. or fraction thereof. |  |  |
| 6 | Roadway Subgrade: Fills and Cuts | Moisture/Density | 1 per every 500 Lane Ft. or fraction thereof, every 2' elevation. Cuts to be scarified to a depth of 1', recondition as needed and recompact. |  |  |
|  |  |  | All final subgrade. |  |  |
| 7 | Roadway (Concrete) | Air/Slump | First 3 loads or until compliance, then every 1,250 C.Y. or fraction thereof. |  |  |
|  |  | Cylinders | 1 set (4) per project for every 1,250 C.Y. or fraction thereof. |  |  |
| 8 | Roadways (Base Coarse) | Moisture/Density | 1 per 500 Lane Ft. or fraction thereof. |  |  |
|  |  | Gradation & Atterberg Limits | 1 per 2,000 Tons or fraction thereof. |  |  |
|  |  | Proof-Roll | Subgrade prior to Base Course placement. Base Course prior to placement of asphalt. |  |  |
| 9 | Roadways (Asphalt) | Density | 1 per 500 Lane Ft. or fraction thereof, per lift. |  |  |
|  |  | Extraction/Gradation | 1 per 1,000 Tons or fraction thereof. |  |  |
| 10 | Roadways (Asphalt & Concrete) | Cores | 1 per 1,000 Lane Ft. or fraction thereof. |  |  |
|  |  | Profil-O-Graph | Minor Arterial classification and above. |  |  |

# Pavement Design Reports

In accordance with Appendix D – Pavement Design Criteria and Report in the Engineering Criteria Manual, all projects, including private roadway, must submit an approved pavement design to El Paso County for review and approval before any roadway construction shall begin.

D.6. - PAVEMENT DESIGN REPORT

The Pavement Design Report shall be prepared by or under the supervision of and signed and seal by a professional engineer registered or authorized to practice in the State of Colorado. The Pavement Design Report shall include the following information:

• Vicinity map to locate the investigated area.

• Scaled drawings showing the location of borings.

• Scaled drawings showing the estimated extent of subgrade soil types and ESAL for each roadway.

• Pavement design alternatives for each roadway on a scaled drawing.

• Tabular listing of sample designation, sample depth, Group Number, Liquid Limit, Plasticity Index, percent passing the No. 200 sieve, AASHTO Classification, Group Index, soil description, and moisture content. Percent soluble sulfate will also be necessary for rigid pavements.

• Identification of any samples that were consolidated to create composite samples for testing purposes.

• CBR or R-value test results of each soil type used in the design.

• Pavement design nomographs properly drawn to show Soil Support - ESAL - SN and/or output from an approved AASHTO pavement design program.

• Design calculations including all design assumptions.

• A discussion regarding potential subgrade soil problems including, but not limited to soils with swelling potential, frost susceptible soils, ground water, drainage considerations (surface and subsurface), cold weather construction (if appropriate), soluble sulfates in the subgrade, and other factors or properties that could affect the design or performance of the pavement system.

• Recommendations to alleviate or mitigate the impact of problems discussed in Item I.

• Pavement Mix Types to be used for the project.

Please contact assigned Inspector (Name/Email) when you are ready to submit your pavement design. They will create a Paving (PAV) file in EDARP where you will submit the approved design for review and approval.

No proof rolls or paving shall take place until the pavement design is reviewed and approved by El Paso County.

Please see the following link to Appendix D for more information: https://library.municode.com/co/el_paso_county/codes/engineering_criteria_manual_?nodeId=ENCRMA_APXDPADECRRE

# Work in the Right-of-Way

A Work in the Right-of-Way Permit is required for obstructing or excavating within any public right-of-way or easement, and for encroaching upon any County right-of-way or easement.

No person may obstruct or excavate any right-of-way or easement or encroach upon any County right-of-way or easement without first having obtained the appropriate Work in the Right-of-Way Permit from the ECM Administrator. In addition, no person may excavate or obstruct the right-of-way or easement beyond the date or dates specified in the permit unless: (1) the person requests a permit extension before the expiration of the initial permit, and (2) a new permit or permit extension is granted.

No work shall begin until a Work in the Right-of-Way Permit has been issued.

Application for Permit

A. Complete Application Required.

1. General. Applicants shall file a complete application for a Work in the Right-of-Way Permit. Each application shall:

• Identify and describe the work to be covered by the permit for which the application is made.

• Describe the land on which the proposed work is to be done, by legal description, street address, or similar description that shall readily identify and definitively locate the proposed work location.

• Be accompanied by plans, diagrams, computations and specifications, and other data as required by these Standards and the approved application and permit checklists.

• Be accompanied by a traffic management plan that clearly describes the traffic management to be implemented and maintained during excavation, obstruction or placement of the encroachment.

• Identify in detail the activities including proposed dates and times of operation, schedule for start and completion.

• Include all other materials requested by the ECM Administrator.

2. Signed by Applicant. All applications for Work in the Right-of-Way Permit shall be signed by the applicant, or an authorized agent, who may be required to submit evidence to indicate their authority.

3. Joint Applications. Applicants may jointly make application for permits to excavate, obstruct or encroach on the County right-of-way at the same place and time. The ECM Administrator may reduce the disruption and degradation portions of the permit fee for applicants who join in during a scheduled obstruction, excavation, or encroachment action whether or not it is a joint application by 2 or more applicants or a single application.

4. Encroachment Removal Agreement. An approved executed Encroachment Removal Agreement is required for any planned encroachment into the County right-of-way or easement. A metes and bounds easement for the encroachment shall be provided to the ECM Administrator with a statement of justification as to why the appurtenance must remain in the County right-of-way or easement.

In the event the County performs work in this area which requires removal of the encroachment, the registrant shall at their own cost remove and relocate the appurtenance, or the ECM Administrator may have the encroachment removed at the County's expense and invoice the registrant.

5. Supplemental Applications. A Work in the Right-of-Way Permit is valid only for the area of the right-of-way or easement specified in the permit. No permit holder may perform any work outside the area specified in the permit, except as provided. Any permit holder that determines an area greater than that specified in the permit must be obstructed, excavated or encroached upon must, before working in that greater area: (1) make application for a permit modification and pay any additional fees, and (2) be granted a new permit or permit modification.

A Work in the Right-of-Way Permit is valid only for the dates specified in the permit. No permit holder may begin its work before the permit start date or, except as provided herein, continue working after the end date. If a permit holder does not finish the work by the permit end date, the permit holder must: (1) make application for a permit extension for the additional time needed before the permit expires, and (2) receive the extension before working after the end date of the previous permit.

6. Determination of Application Completeness. An application will be considered complete if it is submitted in the required form and includes all mandatory information, including all supporting materials specified by the ECM Administrator. If an application is determined to be incomplete, the ECM Administrator shall provide notice to the applicant along with an explanation of the application's deficiencies. No further processing of the application shall occur until the deficiencies are corrected in a resubmittal. An application which is determined to be incomplete may or may not retain its same processing cycle.

B. Plan Submittal Requirements.

1. General. Plans for any work or activity within the County right-of-way or easement shall be submitted to the ECM Administrator for approval. For minor installations such as service lines, drops, etc., simple sketch plans with pertinent information as to location and depth may suffice as the plans.

For complex applications and if requested on the application, the following shall be provided:

• Engineering scale drawings showing the location of all facilities and improvements proposed.

• Location and approximate depth of the subject and related facilities and any other facilities in the immediate vicinity.

• A description of the methods that will be used in the work.

• The County Road and associated right-of-way affected by the work.

• Offset distances from the roadway centerline to the back of curb or edge of pavement surface and the associated right-of-way line.

• A legend explaining symbols, characters, abbreviations, scale, north arrow, and other data.

• The location of any public streets, trails, walks or alleys and private property accesses that will be temporarily closed to use during the work.

• Any facilities to be abandoned, if applicable.

• Any other information required by the ECM Administrator.

2. Traffic Control. Work within the County right-of-way shall not interfere with traffic. If interference with traffic is require, a traffic control plan shall be submitted and approved by the ECM Administrator as part of the permit application. All traffic control shall conform to MUTCD standards.

3. Signed and sealed by PE. The seal of the design engineer shall appear on each sheet. The design engineer shall be a registered Colorado Registered Professional Engineer.

For more information on Work in the Right-of-Way (including expiration and extension, fees, inspections), please see the following link to chapter 5 in the Engineering Criteria Manual:

https://library.municode.com/co/el_paso_county/codes/engineering_criteria_manual_?nodeId=ENCRMA_CH5PEIN_5.5WORI-WPE

Link to apply for permit: https://www.epc-rowpermit.com/

# Stormwater and Erosion Control

Notice to Proceed (NTP) Process

- Contractor to schedule Initial Control Measure Inspection with EPC Stormwater (SW) Inspector at least 48 hours in advance of proposed inspection time.

- Contractor will receive an Initial Control Measure Inspection Report that will summarize findings.

- If there are findings on the reports, Contractor to address findings and then request a reinspection.

- The EPC SW Inspector has the discretion to require the Temporary Sediment Basin (TSB) be installed prior to NTP if it is on the initial grading plans.

- If Traffic Control Measures TCM(s) are to be required in or adjacent to the ROW, the contractor needs to obtain a Work in the ROW Permit.

- EPC SW Inspector will send Stormwater’s Initial Stormwater Control Measure Memo to the Permit Holder(s), Stormwater Inspections Supervisor, and Development Services Inspections Supervisor once all Initial Control Measures have been adequately installed and all required components are included in the SWMP.

- Note that if applicable, an APPROVED & SIGNED PCM Maintenance Agreement is required prior to issuing the Initial Stormwater Control Measure Memo and issuing NTP.

- EPC - DPW - Development Services Inspections team will send the official NTP to the Permit Holder once all Stormwater & Development Services NTP requirements have been met.

Stormwater Management Plan (SWMP) and Inspections

- Contractor to provide SWMP location to the SW Inspector. SWMP may be kept on-site or electronically, however the SW Inspector must have access to review at any time. If the on-site location will include a locking mechanism, EPC must be given access.

- Qualified Stormwater Manager (QSM) to keep Stormwater Management Plan (SWMP) updated. The expectation is that the site map, self-inspections, TCM details etc are kept up-to-date until the permit is terminated. This includes dates of field changes of TCMs, sources of pollution, areas of disturbance, etc. Reference CDPHE COR400000 permit for site map requirements.

- EPC SW Inspector to provide overview of the EPC Compliance Inspection process. Describe info that will be included on inspection reports. Discuss expectation for control measure (CM) maintenance and installation.

- Routine Maintenance: CM still operating in accordance with its design but requires preventative maintenance to prevent failure following a storm event. For sediment control related CMs, this is typically when the CM is at 50% of its capacity.

- Inadequate: CM that is not installed per approved specifications or is not installed to operate in accordance with its design (e.g., one row of silt fence for more than ¼ acre or one sediment trap for more than 1 acre).

- EPC vs. Self-Inspection Inspection Frequencies

- Contractor’s Self-Inspections (by Qualified Stormwater Manager):

- Active site: once every 7 days or; once every 14 days AND within 24-hrs of a storm or snow melt event.

- Inactive site awaiting final stabilization: once every 30 days (until ESQCP is terminated). All ground disturbing activities must be complete and final stabilization measures implemented to be eligible.

- EPC SW Inspections:

- Active site: 1-45 days (1-14 days if there are findings during previous inspection).

- Inactive site awaiting final stabilization: 90 days and more frequent depending on site conditions/weather. All ground disturbing activities must be complete and final stabilization measures implemented to be eligible.

UtiliSync

- EPC Inspectors use UtiliSync to send inspection reports.

- If you are not receiving reports once construction has started, check spam folders or confirm the Inspector has the correct email address.

- If the site is in enforcement and you haven’t been receiving the inspection reports, El Paso County will not be held responsible as it was not notified of the failure to receive such reports.

- Reports are emailed under the subject: “El Paso County Stormwater Inspection – (Site Name)” and include a link to view the full report.

Construction

- Contractor to utilize phasing of soil disturbances, when possible, to minimize disturbance.

- To maintain compliance with ESQCP, recommend prioritizing construction and slope stabilization for Permanent Control Measures (PCMs)/ponds. This will reduce the potential for erosion and offsite discharge.

- Contractor to follow engineering details for all PCM components (e.g., buried riprap, forebays, trickle channels, micropools, micro-screens, orifice plates, gaskets, cutoff walls, etc.) and other PCM components like riprap aprons/rundowns/spillways (filter fabric, rock size, placement, distribution) and check dams.

- The Permit Holder must notify the EPC SW Inspector prior to any installation of buried PCM components, such as cutoff wall, soil riprap, buried riprap, grouted riprap, underdrains, etc., so that the EPC SW Inspector can oversee the installation.

Preliminary & Final Acceptance

- Preliminary Acceptance

- EPC will ensure that stormwater facilities and features are installed per design drawings and are properly maintained.

- Contractor to submit a spec sheet and PO/receipt for the seed mix purchased and used.

- Contractor to submit As-Builts and Pond Certification for review.

- Final Acceptance

- EPC will look for defect warranty/workmanship items to include grading, concrete or metal failures, etc. and that final stabilization requirements have been met.

Permeable Landscape Detention, Rain Gardens and Sand Filter Basins

- Contractor to provide spec sheet for the proposed filter/growing media to be installed prior to delivery (only applicable for Sand Filter Basins and Permeable Landscape Detention/Rain Gardens) so that EPC can verify that it meets spec.

- For these types of PCMs, contractor to minimize compaction of filter/growing media. Consider using a Slinger Truck (or equivalent) to place the media.

ESQCP Termination

- ESQCP Termination is separate from but may coincide with Preliminary/Final Acceptance.

- Permit Holder(s) to request Termination Inspection once they believe termination requirements have been met. Termination requirements are outlined in Appendix I of the EPC Engineering Criteria Manual.

- Permit Holder(s) to provide CDPHE Termination Letter showing that their State permit has been closed prior to ESQCP Termination.

- Once all termination requirements have been met, SW Inspector will send a Permit Termination Memo to the Permit Holder(s).

- Noxious Weeds need to be eradicated or a Noxious Weed Management Plan must be approved by Environmental Services.

ATTACH A COPY OF APPROVED FAE AND ESQCP HERE